## Slide 1: SPM Lab
Lab 2

## Slide 2: Task Types
Fixed Unit tasks
Unit refers to assignment units as percentages. A resource can be assigned to a task 100% or 50% (when resource is available for half of the time only)
Fixed duration tasks
A task that takes specified amount of time even if you have more than one person working on it.
Fixed work tasks
If 1 person takes 4 days to do a Job and if you assign 2 people that means job gets done in 2 days
Effort driven
By default all fixed work tasks are effort driven.

## Slide 3: Task Dependency
Finish to start FS
First part is the related to predecessor and next part to successor. This is most common the predecessor task must finish before the successor task can start. This is created by using the link buttons on taskbar.
Start to start SS
Successor cannot start until predecessor starts
Finish to finish FF
the successor task cannot finish until predecessor
Start to finish SF
successor task cannot finish until predecessor task starts.

## Slide 4: Activity 2
Create a gantt chart with the following specifications:
Project name: AVL software
Company : Softech
Make summary visible
Set calendar to : week start : Monday , year starts in : January, office working hours : 9 to 6 , 8 working hours per day and 48 working hours per week, 24 days per month.
All the tasks are Fixed Work Task

## Slide 5
1. Requirement phase:
A. Requirement gathering from client -> no dependency
B. Requirement gathering from end users -> SS -> A
C. Requirement analysis -> FS-> A, B
D. Requirement specification -> FS -> A, B, C
E. SRS inspection -> FS -> D
F. Update manual -> SF -> E
2. Design phase
G. Design front end -> FS -> E
H. Design back end -> SS -> G
I. Design database -> SS->H
J. Design document creation -> SS -> G, H,I
K. Design document inspection -> FS -> J
L. Update manual -> SF -> K

## Slide 6
3. Coding phase
M. Coding front end -> FS -> K
N. Coding back end -> SS -> M
O. Creating database -> SS-> N
P. Integrating database -> FS-> O
Q. Code inspections -> FS -> M, N, P
R. Code walkthroughs -> SS-> Q
S. Update manual -> SF -> R
4. Testing phase
T. Unit testing -> FS -> R
U. Integration testing -> FS -> T
V. Database testing -> SS -> T
W. System testing -> FS -> U
X. Test report generation -> SS-> T, U, V, W
Y. Test report inspection -> FS -> X
Z. Update manual -> SF -> W

## Slide 7
5. Deployment phase
A1. Generate configuration document -> FS -> Y
A2. Generate user manual -> FS-> F, L, S, Z
A3. Generate SRS document -> FS-> E
A4. Generate design document -> FS -> K
A5. Generate test reports -> FS -> Y
A6. Generate contracts -> FS-> A
A7. Verify all deliverables -> SS-> A1, A2, A3, A4, A5, A6
A8. Installation -> FS-> A7
A9. Client conformance FS-> W, A8
6. Maintenance phase
A10. Corrective maintenance -> FS-> A8, A9
A11. Re-engineering -> FS-> A10
A12. Perfective maintenance -> SS-> A10
A13. Re-engineering -> FS -> A12
A14. Adaptive maintenance (if any) -> SS-> A10, A12